## Project Risk Register
Biodiversity Challenge Funds Risk Register
Lead organisation:
Project ref:
Project title:
Start date:
End date:
Risk contact:
Last update:
Risk Description | [5 empty] | Inherent Risk |  |  | Risk Mitigation |  |  | Residual Risk |  | Updates
| A short name for the risk | New/Emerging, Open, Closed | Briefly: the cause of the risk, the risk itself, and the impact of the risk | Identify risk against the 6 Risk Types | Name, job title and organisation | The likelihood of the risk materialising | The impact if the risk materialises | (autocalculated) |  | Any actions or controls to respond/mitigate the risk | The likelihood of the risk materialising | The impact if the risk materialises | (autocalculated) | See guidance
Date Added | Risk Name | Risk Status | Description of risk | Risk Type | Risk Owner | Probability | Impact | Risk Rating | Risk Response Type | Mitigating Action | Probability 2 | Residual Impact | Risk Rating4 | What's changed this quarter

## Notes on Risk
Biodiversity Challenge Funds Risk Register Template
Please read the Risk Guidance before completing your risk register
Enter one risk per row. Do not leave blank rows between risks.
Risk Description | Date Added | Enter in the date that you added the identified risk into this register using the format: DD/MM/YYYY. The risk date does not change, it remains as a historical record of when the risk was first identified.
| Risk Name | Give your identified risk a succinct single sentence title. For example: COVID -19 impact on PPE supplies
| Risk Status | What is the status of the identified risk, is it: - New / Emerging means that it has not been fully realised as a present risk but is on the horizon and gaining momentum. - Open means that it is present and/or ongoing. - Closed means that it the risk materialised/did't materialise and is no longer relevant or has been resolved, Please choose the risk status from the drop down menu in this column.
| Description of risk | Describe the risk succinctly in 1-3 sentences with a good, clear understanding of the three key elements of a risk: - the cause of the risk - the risk event or situation itself - the impact of the risk on the project
| Risk Type | Six risk types are of interested: A contextual risk is one that is present in the space and location in which you are working. For example, risks may arise in challenging external settings such as conflict-affected areas, economically or environmentally fragile areas, or politicised settings. A delivery risk is a situation or event that will impact you or your partners' ability to deliver the programme. For example, the low resource capacity of your implementing partner(s) could prevent the programme from delivering against its stated objectives. Other delivery risks may arise around procurement disruptions or technical hurdles. This is likely to be higher for innovative or high impact projects. A safeguarding risk is an occurrence that could pose a threat to the protection of the health, well-being and human rights of individuals, which allow people — especially children, young people and vulnerable adults — to live free from abuse, harm and neglect. Every project should record at least one safeguarding risk. An operational risk relates to internal capacity to effectively oversee implementation of the project and duty of care to staff, inlcuding professional competence, experience and appropriate level of resource in managing the project and funds. An example could be that staff are exposed or not adequately protected from infectious diseases within their work. A fiduciary risk is one that arises when funds are not used for the intended purposes; do not achieve value for money; and/or are not properly accounted for within the project. Risks such fraud or misappropriation are recorded within this category, as are exchange rate fluctuations or other financial management issues. All projects should record at least one fiduciary risk. A reputational risk is one that will pose detriment to the organisation's reputation or public image due to certain activities, associations, or perceptions. Please choose the relevant risk category from the drop down menu in this column.
| Risk Owner | Who is the owner of the risk? Who is responsible for monitoring and taking action on this identified risk? The person could be within your organisation or within your downstream implementing partner organisation. There can only be one risk owner per risk. Enter their full name, their job title and specify which organisation they are from.
Inherent Risk | Probability | The Inherent Risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. Rare (<5%) - May occur only in exceptional circumstances Unlikely (>5%<20%) - Could occur at some time Possible (>20%<50%) - Might occur at some time Likely (>50%<80%) - Will probably occur in most circumstances Almost certain (>80%) - Is expected to occur in most circumstances Please choose the probability risk rating from the drop down menu in this column.
| Impact | Inherent Risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. Insignificant - Easily handled with almost no impact on project outcomes / objectives Minor - Causes some rework or reassessment in limited areas, with limited impact on project outcomes / objectives Moderate - Causes additional work and reassessment but impact on project outcomes / objectives is containable Major - Causes significant rework, modification or reassessment of project to avoid one or more project outcomes / objectives being unmet Severe - Causes failure of project to meet outcomes / objectives, or closure of project Please choose the impact risk rating from the drop down menu in this column.
| Risk Rating | Inherent Risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. It is determined by the Probability and Impact rating, and will be automatically calculated to be one of the following: Minor - Limited reduction in outcomes if this occurs Moderate - Higher but still limited loss in outcomes if this occurs Major - Outcomes reduced if this occurs but some important outcomes still likely Severe - Very significant reduction in outcomes when this occurs
Risk Mitigation | Risk Response Type | Responses to risk can be categorised in to one of the following. Types of risks that may negatively affect (threats) the project’s ability achieve its outcomes: Avoid - Make the uncertain event certain Reduce - Change the impact and/or probability of the threat Transfer - Ownership maintained but part of the risk transferred to a third party Share - Multiple parties share the risk on a pain/gain share basis Accept - Threat accepted, including the full impacts if the risk materialises, but do not take any further action Prepare contingent plans - Threat accepted for now but with a contingent plan if the situation changes Types of risks that may positively affect (opportunities) the project’s ability achieve its outcomes: Exploit - Make the uncertain event certain by taking appropriate action Enhance - Change the impact and/or probability of the opportunity Transfer - Ownership is maintained but part of the risk is transferred to a third party Share - Multiple parties share the risk on a pain/gain share basis Accept - Accept that the opportunity might be realised but do not take any further action Please choose the action from the drop down menu in this column.
| Mitigating Action | Detail the actions that the risk owner(s) will take to mitigate against the risk and if there are any controls that can be put in place or exercised to manage the risk. Example entry: An inventory of existing PPE has been created to understand how much the company currently holds. Various PPE materials have been grouped together to be stored as full sets for an individual. This will be used to determine the number of PPE sets against the number of staff needing PPE. The number of rotating frontline staff will be reduced in the interim until enough PPE can be procured to ensure all staff are safe when on duty.
| Probability | The Residual Risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurence or impact. Rare (<5%) - May occur only in exceptional circumstances Unlikely (>5%<20%) - Could occur at some time Possible (>20%<50%) - Might occur at some time Likely (>50%<80%) - Will probably occur in most circumstances Almost certain (>80%) - Is expected to occur in most circumstances Please choose the probability risk rating from the drop down menu in this column.
Residual Risk | Impact | The Residual Risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurence or impact. Insignificant - Easily handled with almost no impact on project outcomes / objectives Minor - Causes some rework or reassessment in limited areas, with limited impact on project outcomes / objectives Moderate - Causes additional work and reassessment but impact on project outcomes / objectives is containable Major - Causes significant rework, modification or reassessment of project to avoid one or more project outcomes / objectives being unmet Severe - Causes failure of project to meet outcomes / objectives, or closure of project Please choose the impact risk rating from the drop down menu in this column.
| Risk Rating | The Residual Risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurence or impact. It is determined by the Probability and Impact rating, and will be automatically calculated to be one of the following: Minor - Limited reduction in outcomes if this occurs Moderate - Higher but still limited loss in outcomes if this occurs Major - Outcomes reduced if this occurs but some important outcomes still likely Severe - Very significant reduction in outcomes when this occurs Please choose the overall risk rating from the drop down menu in this column.
Updates | What's changed this quarter | Risks should be regularly reviewed, quarterly, and updates should form a brief summary of what has changed since the risk was entered originally. Have any event(s) occured that led to the risk increasing, decreasing or remaining steady in rating? How has the wider risk context changed in the meantime? Have new mitigations been undertaken since the last update? If the risk is being closed, what led to it being resolved? This 'What's changed' column does not need to be filled in when you add in a new risk to the register. The new entry should be dated, and all previous entries should be left in the cell for a historical record with the most recent entry at the top of the cell. Example entry: 16/07/2020: COVID-19 continues to impact on the local availability of various supplies needed for the project, including PPE. However, a supplier in the neighbouring country has now been identified and contacted to determine if an order can be placed and shipped across the border. 17/05/2020: The rates of COVID-19 have increased significantly across the country and the government has imposed movement restrictions. This is impacting on the local availability of various project supplies, which may start having an impact on project delivery. We are starting to explore alternative sources. 14/01/2020: The new coronavirus is spreading quickly in neighbouring countries and the first cases have been identified in the capital city. We are keeping monitoring the rates and locations of infection on a daily basis.

## Delivery Chain Risk Map
Biodiversity Challenge Funds Delivery Chain Risk Map
| Tier 0 Darwin Initiative/IWTCF/Darwin Plus |  |  | Flow of funding
| Tier 1 Fund Manager (NIRAS) |  |  | Lines of Reporting and Accountability
Tier 2 Lead Partner
| Organisation Name: | Total funds in £GBP to the Lead Partner | Identified risks at Tier 2 level | Controls and mitigations for identified risks
Tier 3 Project Partner(s)
(please specify if risk outlined is only relevant to a particular partner)
| Organisation Name: | Total funds in £GBP for each Project Partner | Identified risks at Tier 3 level | Controls and mitigations for identified risks
Tier 4 Project Partner(s)
Please specify if risk outlined is only relevant to a particular partner.
| Organisation Name: | Total funds in £GBP for each Project Partner, and name of Tier 3 organisation providing the funds | Identified risks at Tier 4 level | Controls and mitigations for identified risks

## Notes on DCRM
Biodiversity Challenge Funds Delivery Chain Risk Map Template
Please read the Risk Guidance before completing your Delivery Chain Risk Map
Delivery Chain Risk Mapping
Delivery Chain Risk Mapping (DCRM) is a useful tool for risk management in monitoring processes and improve understanding of how funding flows throughout a delivery chain, to ensure that programmes achieve their objectives. With this understanding we can: - Understand a delivery partner’s role in achieving the Outcome and opportunities for potential scale up. - Capture and manage risks that could affect the Outcome. - Ensure risks are being managed by those best placed to do so. - Strengthen our programme management capacity and delivery
DCRM is a visual depiction in understanding, capturing, and managing the risks to the successful delivery of a programme, in relation to downstream delivery partners. It should, where possible, identify all partners (funding and non-funding e.g. legal/contributions in kind) involved in the delivery of the project. Delivery chain risk mapping captures details of: - The name of all downstream delivery partners and their functions. - Funding distributed to each delivery partner. - High level risks involved in programme delivery, mitigating measures and associated controls.
A good delivery chain risk map will: - Provide a clear understanding of all delivery partners involved in the delivery of a programme and the relationships between them. - Identify key delivery risks, mitigating measures and associated controls throughout the delivery chain. - Help ensure suitable risk management throughout the delivery chain.
As they are part of the Risk Framework, maps should be reviewed and updated periodically, with any material changes recorded as soon as possible.
Biodiversity Challenge Funds Projects: Projects will need to complete, either as part of their application (Darwin Initiative Extra, IWT Challenge Fund Extra, and Darwin Plus Strategic) or prior to award of a grant, the delivery chain risk map template if they are recommended for a grant. The delivery chain risk map captures risks specific to the delivery model and tiered funding structure. There may be some risks should be captured in both risk register and delivery chain risk map. For example, there may be delivery chain risks that could impact on the overall project outcome if they materialised, but not all delivery chain risks need to be duplicated in the project risk register. There should however be at least one overarching and high-level delivery chain risk that records the overall risk associated with your delivery model, whether that is direct implementation or through delivery partners.

## Issue Register
Biodiversity Challenge Funds Issue Register
Issues are relevant events (including materialsied risks) that have occurred, but which were not planned and require management action after the project has started. As such this table is not needed during the planning phase, only once the project starts and the first issue is identified.
Issue | [5 empty] | Action
Date Added | Issue name | Issue description | Priority | Severity | Issue owner | Status | Action

## Notes on Issues
Biodiversity Challenge Funds Issue Register Template
Please read the Risk Guidance before completing your issues register
Enter one issue per row. Do not leave blank rows between issues.
Issue | Date Added | Enter in the date that you added the identified the issue into this register using the format: DD/MM/YYYY. The date does not change, it remains as a historical record of when the issue was first identified.
| Issue Name | Give your identified issue a succinct single sentence title.
| Issue Description | Describe the issue succinctly in 1-3 sentences with a good, clear understanding of the three key elements of am issue: - the cause of the issue - the event or situation itself - the impact of the issue on the project
| Priority | Is your issue a Low, Medium or High priority? Please choose from the drop down menu in this column.
| Severity | What is the assessed impact of the issue on the project if noaction is taken: Minor - Limited reduction in outcomes if this occurs Moderate - Higher but still limited loss in outcomes if this occurs Major - Outcomes reduced if this occurs but some important outcomes still likely Severe - Very significant reduction in outcomes when this occurs Please choose from the drop down menu in this column.
| Issue owner | Who is the owner of the issue? Who is responsible for monitoring and taking action on this identified issue? The person could be within your organisation or within your downstream implementing partner organisation. There can only be one owner per issue. Enter their full name, their job title and specify which organisation they are from.
Action | Status | Is the status of the issue: Open - the issue is being monitored, but no actions are being taken Investigating - the issue is under investigation to understand it, and develop the response Implementing - the response to issue is being implemented Escalated - the issue has been brought to the attention of more senior staff, partner or funder (Defra) Resolved - the issue has been resolved or is no longer considered an issue Please choose from the drop down menu in this column.
| Action | Describe your action to mitigate or resolve the issue, including escalation decisions, with a brief summary of any activities taken since the last update. Have any event(s) occured that led to the issue increasing, decreasing or remaining steady in priority or severity? How has the wider context changed in the meantime? Have new mitigations been undertaken since the last update? If the issue is being closed, what led to it being resolved? Any entry should be dated, and all previous entries should be left in the cell for a historical record with the most recent entry at the top of the cell.

## Dropdown lists (hidden)
Impact | Probability | Risk Response Type | Category
Insignificant | Rare | Threat - Avoid | Contextual
Minor | Unlikely | Threat - Reduce | Delivery
Moderate | Possible | Threat - Transfer | Safeguarding
Major | Likely | Threat - Share | Operational
Severe | Almost certain | Threat - Accept | Fiduciary
|  | Threat - Prepare contingent plans | Reputational
|  | Opportunity - Exploit | Other
Trend | Status | Opportunity - Enhance
Steady | New/Emerging | Opportunity - Transfer
Upwards | Open | Opportunity - Share
Downwards | Closed - the risk materialised | Opportunity - Accept
Closed - the risk didn't materialise
Priority |  | Issue Status
Low |  | Open
Medium |  | Investigating
High |  | Implementing
Escalated
Resolved